NCDXA 2012 DX Convention Proposal
After a 20 year hiatus, the leadership of the National Capitol DX Association would like to resurrect the old DXPO convention.  K3LP and W3MC have done a little preliminary work, and would like to present the following proposal for discussion at our December meeting.  We have found a suitable site and have contacted a number of presenters for the event which are listed below.  Date will be Saturday, 25 August, 2012.  Location will be the Holiday Inn & Conference Center at the FSK mall in Frederick MD.
THE PROGRAM

ARRL DXAC Forum (tentative)

K3LP

Ethiopia Ham Radio Youth Development Project

K3ZO

(Subject TBD)

N6PSE

ST0R DXpedition

W3LPL
Contesting & DXing

W6OAT
How DX Clubs can be Value-Added Members of DXpeditions?

YT1AD
3D2R Ham Radio Youth Development Project

We have room for one, or maybe two, more speakers.  
THE VENUE

The hotel in Frederick is well suited for hosting events such as this.  After a visit to the site and speaking with their conventions manager, we have the following cost proposal from the hotel, based on 100 in attendance:

Ballroom rental
$1400


Banquet 

$3300


Morning coffee
$ 150


Bartender in room
$ 150


Total Hotel Fee
$5000

Other expenses will include approximately $2000 for audio-visual support for the presentations, and another $500 or so for miscellaneous expenses like postage, advertising, bank fees, setting up on line registration.  We have a written proposal from the Holiday Inn; other expenses are estimated, based on experience from W9DXCC in Chicago.   The Northern Illinois DX Association treasurer was kind enough to share their financial information with me, to assist in preparing our budget.

THE BOTTOM LINE
With estimated expenses of $7500, we will need at least 100 paid attendance at $75 to break even.  Some careful negotiating, and membership donations of services will certainly bring the total cost down.  
WE NEED HELP IN THE FOLLOWING AREAS

To do this project successfully, we need a long term, dedicated effort by a few people to take charge of certain phases, recruiting extra help as needed. The two biggest jobs, general chairman (W3MC) and program chairman (K3LP & W3MC) are already taken care of.  There are still a few more areas which need immediate attention:

1.) Advertising -.  Web page, on line ads, magazine ads, club newsletter ads, word of mouth, putting slips in QSO cards (like NCDXF does).  Bernie has already offered to plug us in QST and his email publications.  This needs to start now.
2.) Registration - We need someone to handle on line and mail in registrations starting as soon as we announce the event.  Then, we need a couple guys to sit behind a table and check in folks on Saturday morning - maybe Friday night, too.

3.) Door Prizes and Raffle - lots of prizes - scare up all the goodies we can to give away.  Not just radio stuff.
4.) AV for presentations - we need a trained professional for this - someone who does it for a living.  We must have a club member with some experience, or link to a trained professional in this field?  We need to go first class with this.
Events like this are not only great fun, but can be very educational  for both experienced and beginning DXers.  I look forward to a healthy discussion of this at our December meeting.
73,

Mike Cizek W3MC
PAGE  
2

